## Review List
R E V I E W L I S T (Note: Pls use MS Word reviewing tools, so we can add in all our thoughts.) | Responsible colleague | Receiving Colleague | Ideal TimeFrame (Starting Date) | Ideal TimeFrame (Finishing Date) | Nature of Commitment / Beneficiary | TUL 500 Writings | TUL 520 Urban Spirituality | TUL 530 Church Planting | TUL 505 Language &Culture | TUL 540 Urban Reality | TUL 655 Advocacy& Environment | TUL 555 Educational Centre Devt | TUL 630 Community Transformation | TUL 550 Service to the Marginalized | TUL 640 Entrepeneural &Organizational Leadership | TUL 570 Field Supervision | TUL 620 Urban Leadership Movements | Theory &Prac Community Economics | Doing Hermeneutics for the Poor | Intro to Bible Revelation | Doing Theology Among Urban Poor
1. Get the inital draft of the course outline in by end of week (as we can). | Lee/ Grace | send to Viv | 2007-09-01 | 2007-09-05 | All committed in April | in | in | in | in | in | in | missing | missing | missing | Bryan doing | in | in | in | missing | in | missing
2. To review initial draft. | Lee/Grace / Jessie/Paul | send to Viv | 2007-09-01 | 2007-09-05 | All committed in April
3. To review draft in relationship to the other schools w/editorial comment for each school & a generic course. (5.1) Viv to review drafts in comparison to other schools. (5.2) Identifying best course goal definition. (5.3) Seeking to upgrade learning outcome definitions to MA level. (5.4) Return them to each school w/other editorial comment. (5.5) Do 1 generic course for the web &for submission to APU. | Viv | send to Lalaine / Viv | 2007-09-01 | 2007-09-10 | Viv to each school; for all &web delivery.
4. To reformat. | Lalaine | send to Lee/Grace / Rich / Viv | 2007-09-05 | 2007-09-12 | Lalaine for all.
5. Discussion of comments, plus evalute how ti relates to churchplanting movemnts, male/female perspectives, quality of theological component. | Corrie/Grace/Jessie/Writers | send to Viv | 2007-09-05 | 2007-09-20 | Each school.
6. To add in the actual lecture titles and readings for each hour &activities from each school (Is this timeline realistic?). | Writers | send to Viv | 2007-09-01 | 2007-09-30 | Upgrades coursewriters skills&delivery; good for all schools.
7. To integrate in a generic design for web. | Viv | send to web. Viv to Rich. | 2007-09-30 | 2007-10-15 | Brings completion to course outlines. Integration for all &the web. Needed for APU.
8. To scan a set of readings into a class set as jpeg files for uploading on web. | Writers | send to Lalaine/Viv | Before class delivery / as they come. | As we are able. | Good practice for each school; for common web delivery.
9. Develop the course manuals with lectures and activities outlined. | Writers | Send to Viv |  | by end of course
10. Viv Add these to web | Viv

## Process
S T A T U S L I S T as of 25/9/07 Code, yellow being integrated, orange, nearly there, green, largely done, red: problems to complete, pattern means currently working on this as priority | TUL 500 Writings, Reign of God, Urban Realities | TUL 505 Language &Culture | TUL 520 Urban Spirituality | TUL 530 Church Planting | TUL 540 Urban Reality | TUL 550 Service to the Marginalized | TUL 555 Educational Centre Devt | TUL 560 Community Economics | TUL 570 Field Supervision | TUL 620 Urban Leadership Movements | TUL 630 Community Transformation | TUL 640 Entrepeneural &Organizational Leadership | TUL 650 Primary Health Care | TUL660 |  |  | TUL 655 Advocacy& Environment C. Relief & Devt | TUL 670 Integration Seminar | Doing Hermeneutics for the Poor | Bible | TUL501 Doing Theology Among Urban Poor
[14 empty] | Field Supervision | TUL 655 Advocacy& Environment | TUL 655 Advocacy& Environment B. Land Rights |  |  |  | and Christian Vision = Writings, Reign and Reality
A T S | Regular ATS course. Hard copy received. Need soft copy. | Draft written, comments made, response forthcoming. | Already taught by Viv. Done | Meet with Raineer and Mars 9/5. No syllabus yet. | Final from Jun | Patrick asked to be head course writer 9/5 | 1st draft comments sent to Chona. Final forthcoming. | Gavin and Art working on this course. Final arrangements need clarification. | 1st draft comments sent back to Aaron. A few final revisions being made. | Assigned to Viv/Joetique. Viv's up on web. Joetique to submit 2nd week Sept. | Assigned to Jun (Lead Faculty), Boy, David, Mel, Joetique. No syllabus. | 1st draft comments sent to Rene. Minor revisions needed. | 1st draft comments sent to Alice. Minor revisions needed. | as in 570 | 1st draft comments sent to Joy. Minor revisions needed. | Raineer | 1st draft comments sent to Joy. Minor revisions needed. | Lee will develop at a later date. | Larry to Develop. No copy. | Syllabus done. | Regular ATS course with focus in assignments on urban poor. Boy to teach. No copy.
H B I | Rob has done but not completed | Combined Dr. Saravanan's with Rich. | Varghese Thomas done, revising . | NA (Viv) | Dr. Manokaran submitted final draft; waiting for feedback. | Christopher Baskeran working on it. | Mrs Darsini Edward working on it., 3 pages of notes | Jasmine Inbaraj submitted 1st draft; working on the corrections. |  | Paul Gupta working on it. | Jessie Nesakumar working on it. | MJ John working on it. | Chris Baskeran sent |  |  |  |  | Paul Cornelius & Jessie Nesakumar working on it. |  | Rob developed this for them | Paul Cornelius working on it.
A P U |  | Done by Rich | Sent to Rich | Sent to Rich | Sent partially integrated to Rich |  |  |  | Rich Completed |  |  |  |  | Rich Completed |  |  |  | Rich Completed |  |  | Received 3 page syllabus
Integrated by Viv, green means all content is there, yellow means mostly there, being formatted, red means serious trouble | Integrated Robs, Need to integrate book list from ATS | Combined Dr. Saravanan's with Rich. | On Web | On web, raineer has developed sme alternatives need to review | Integrated but need to review all readings per lecture | Nothing received, have workbook from ACTION on street kids, but nothing on drug addicts | Chonas 3rd version received Received, Johns received, HBI sktch draft rcd Integrated but incomplete ovocational | Integrated, on web, waiting updatee from HBI on readings and assessments | Rich On Web | On Web, waitig for Boby and Joetique to revise | Intial draft from Jun Manalo, Checked Corrie, HBI. ATS looking at it again, Done a draft of possible structure for all | In process by Tuesday 25, received from Rene 24th. Decided to keep as separate courses | , Chris new version to be integrated, received the ATS version but it is missing HIV/AIDS All three on web | Rich Completed Received from Aaron, need to review Aarons | Nearly Integrated | on web | Rob to complete | Rich Completed | Reveived from Larry,, sent to Lalaine for formatting | Received, not up to standard in terms of content or formatIntegrate Booklist into master course | Received, not up to standard in term sof content and format Review and add materials
To Wendy/Rich |  | to Rich | to Rich | To Rich | to Rich |  | Integrated Sent to rich. Needs major work | to Wendy | to Rich | to Rich | Integrated half done courses to Rich, suggested Bob Moffit for practicum | Sent both Bryans and Renes courses to Rich | Did comparison of three courses, sent to Rich. | minor edits to Rich | to Rich | to rich | Needs Robs books | Rich Completed
Content Check List
Overall | [11 empty] | Bryans, wait for Renes |  |  | Need to integrate Rich contribution
Heading |  |  |  | yes |  |  | yes | yes |  | yes | y | y |  |  | yes | yes | yes
Generic School Title | y |  |  | yes |  |  | yes | yes |  | yes | y | y |  |  | yes | yes | yes
All Main headings are in Document & Formatted |  |  |  | yes |  |  |  | yes |  | yes | y | y |  |  | yes | yes | yes
Has facilitators and course writers names and emails | [7 empty] | yes |  | yes |  | y |  |  | yes | yes | yes
I. Course Description | [6 empty] | yes |  |  | yes |  |  |  |  | yes | yes | yes
4-6 lines |  |  |  | yes |  |  | yes | yes |  | yes |  | y |  |  | yes | yes | yes
Compatible with Rich, Lee and database | [6 empty] | yes | yes |  | yes |  | y |  |  | yes | yes | yes
Good English | [6 empty] | yes | check |  | yes |  | y |  |  | yes | yes | yes
Key Ideas represented | [6 empty] | Missing most of vocational training course | yes, but lacks clarity re basic bookkeeping |  | yes |  | y |  |  | yes | yes | yes
Links to key ideas in expanded Course Rationale | [7 empty] | yes |  | yes |  | y |  |  | yes | yes | yes
II. Course Rationale | [9 empty] | yes |  | y |  |  | yes | yes | yes
Covers main ideas |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | yes | yes | yes
Links to prerequisites or subsequent courses |  |  |  | no |  |  |  | need to add |  | yes |  | y |  |  | Need to link to Urban Realities & CO in Community Transformation | none needed | none needed
Short English phrases |  |  |  | yes |  |  |  | yes, but need to de-Indianise |  | yes |  | y |  |  | yes | yes | yes
Comprehensible |  |  |  | yes |  |  |  | yes |  | yes |  | need edit |  |  | yes | yes | yes
Relates course to Churchplanting |  |  |  | yes |  |  |  | no |  | yes |  | y |  |  | no | no | no
Emphasis on Theology and Practice |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | yes | yes | yes
III. Student Learning Outcomes | [9 empty] | yes
5-7 Outcomes |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | 3 | 3 | 3
Head, Heart Hands |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | yes | yes | skill
Graduate Level not undergrad outcomes |  |  |  | check |  |  |  | yes |  | yes |  | Needs a one page summary of topics to show the rational flow of ideas |  |  | need to check | need to check | need to check
Measurable outcomes (to be defined later) |  |  |  | yes |  |  |  | not yet |  | yes |  | y |  |  | yes | yes | y
Not wordy in definition |  |  |  | yes |  |  |  | yes |  | yes |  | wordy |  |  | yes | yes | y
IV. Course Materials | [9 empty] | yes
3-5 Core texts |  |  |  | yes |  |  |  | t be identified |  | yes |  | too many |  |  | y | y | n
In APA format |  |  |  | yes | [5 empty] | yes |  | nees to be put into Endnote then redone |  |  | y | y | y
V. Course calendar & Activities | [9 empty] | yes
1. Teaching | [9 empty] | yes |  | y
Does not have dates but class 1,2,3, etc |  |  |  | yes |  |  |  | to be developed |  | yes |  | y |  |  | y | y | y
Each class has its assignments/readings. If not highlight |  |  |  | yes |  |  |  | no |  | yes |  | y |  |  | to do | to do | to do
Has 40 hours of material |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | y | y | y
Format is not table like Viv, but like Riches |  |  |  | no |  |  |  | no |  | vivs |  | Viv |  |  | vivs | vivs | vivs
2. Practicum |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | y | y | y
3. Integration Day |  |  |  | yes |  |  |  | no |  | yes |  | y |  |  | y | y | y
VI. Assessment Activities | [9 empty] | yes |  | y
In table format |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | y | y | y
With possible marks and % in 3 columns |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | y | y | y
Add up to 100% |  |  |  | yes |  |  |  | yes |  | yes |  | y |  |  | yes | yes | y
Shows how these will be assessed |  |  |  | yes |  |  |  | no |  | yes |  | y |  |  | yes | yes | weak
Includes week of course |  |  |  | yes |  |  |  | no |  | yes |  | y |  |  | yes | yes | yes
Assessment matches outcomes above |  |  |  | yes |  |  |  | no |  | yes |  |  |  |  | yes | yes | yes
VII. Expectations and grading (Leave this out as in Degree handbook and included in above table)
Includes processes from each of three schools (leave out) | [14 empty] | no | no | no
VIII. Course Policies (delete as covered in degree material not at course level)
VII. Bibliography | [7 empty] | yes |  | y |  | y
all in APA |  |  |  | yes |  |  |  | yes |  | y |  | Need to be put into Endnote to check |  |  | yes | need editing dates | missing biblio
Alphabaetical or by category |  |  |  | yes |  |  |  | yes |  | y |  | y |  |  | yes | yes | yes
Relevant |  |  |  | yes |  |  |  | yes |  | y |  | y |  |  | yes | yes | missing for pt 3
Recent or significant |  |  |  | yes |  |  |  | yes but need to add Busseau |  | y |  | y |  |  | Need more on process of advocacy and community organisation - added a couple | many old ones - deleted | missing
Not more than 25 |  |  |  | yes |  |  |  | yes |  | y |  | y |  |  | yes | too many - deleted many | missing
VIII. Outcome Profile elements from database |  |  |  | to b added |  |  |  | to be added |  | to do |  | to be added
Import from database and format, elimnate irrelevant | [9 empty] | to do
Go through and evaluate if these will be met. | [9 empty] | to do
Add extra to database
Ask for Womens perspectives in the course
Wendys Check List
Draft Syllabus Received | 2007-09-11 | 2007-09-07 | 9/11/2007 *Notes in brackets *Incomplete outline of topics | Not yet received. | 9/11/2007 *Two versions of topics. *Learning outcomes need to be condensed | Not yet received. | Not yet received. |  | 2007-06-29 | 9/11/07 *Missing Filipino, Indian readings, Course Calendar. *Too many outcomes, need editing | Not yet received. | Not yet received. | 2007-09-07 | Not yet received. | Not yet received. | 2007-08-22
Final Syllabus Received
Final Syllabus Reformatted
Draft New Course Form Completed | 2007-09-12 | 9/12/2007 *Outcomes need condensing? | 9/14/07 *In progress. *Need to condense assignment desciptions | [5 empty] | 2007-09-12 | 9/14/07 *In progress. *Anything in brackets are my notes or additions. *Outlines of topics, are long needs editing? *Need to input course assignments. |  |  | 2007-09-14 |  |  | 2007-09-12
Final New Course Form Completed |  |  |  |  | 9/14/07 *In progress. *Need course assignment descriptions *Synthesis Learning Outcomes *Synthesis Activities to Assess Learning Outcome

## Lalaine Editing Check
Editing Check List | TUL 500 Writings, Reign of God, Urban Realities | TUL 505 Language &Culture | TUL 520 Urban Spirituality | TUL 530 Church Planting | TUL 540 Urban Reality | TUL 550 Service to the Marginalized | TUL 555 Educational Centre Devt | TUL 560 Small Business Development | TUL 570 Field Supervision | TUL 620 Urban Leadership Movements | TUL 630 Community Transformation | TUL 640 Entrepeneural &Organizational Leadership | TUL 650 Primary Health Care | TUL660 | TUL 655 Advocacy& Environment | TUL 670 Integration Seminar | Doing Hermeneutics for the Poor | Bible | Doing Theology Among Urban Poor
[14 empty] | Field Supervision |  |  |  | and Christian Vision
A T S | Regular ATS course. Hard copy received. Need soft copy. | Draft written, comments made, response forthcoming. | Already taught by Viv. Done | Meet with Raineer and Mars 9/5. No syllabus yet. | Final from Jun | Patrick asked to be head course writer 9/5 | 1st draft comments sent to Chona. Final forthcoming. | Gavin and Art working on this course. Final arrangements need clarification. | 1st draft comments sent back to Aaron. A few final revisions being made. | Assigned to Viv/Joetique. Viv's up on web. Joetique to submit 2nd week Sept. | Assigned to Jun (Lead Faculty), Boy, David, Mel, Joetique. No syllabus. | 1st draft comments sent to Rene. Minor revisions needed. | 1st draft comments sent to Alice. Minor revisions needed. | as in 570 | 1st draft comments sent to Joy. Minor revisions needed. | Lee will develop at a later date. | Larry to Develop. No copy. | Syllabus done. | Regular ATS course with focus in assignments on urban poor. Boy to teach. No copy.
H B I | Rob has done but not completed | Combined Dr. Saravanan's with Rich. | Varghese Thomas done, revising . | NA (Viv) | Dr. Manokaran submitted final draft; waiting for feedback. | Christopher Baskeran working on it. | Mrs Darsini Edward working on it. | Jasmine Inbaraj submitted 1st draft; working on the corrections. |  | Paul Gupta working on it. | Jessie Nesakumar working on it. | MJ John working on it. | Working on it. |  |  | Paul Cornelius & Jessie Nesakumar working on it. |  |  | Paul Cornelius working on it.
A P U |  | Done by Rich | Sent to Rich | Sent to Rich | Sent partially integrated to Rich |  |  |  | Rich Completed |  |  |  |  | Rich Completed |  | Rich Completed
Integrated by Viv |  | Combined Dr. Saravanan's with Rich. | On Web | On web | Partially integrated. | Nothing received. | Nothing received. | Integrated, on web. | Rich On Web | On Web, waitig for Boby and Joetique to revise. | Nothing received. | Nothing received. | Integrated, on web | Rich on Web | Nearly integrated. | Rich on web
Lalaine formatting checklist
0. All Headings formatted
Number of Units is Correct
Title correct and right size
Spelling Check and conversionof English to American
Course writers names and emails correct
I. Course description
4-6 lines
III. Head Heart hands
bulleted, indented
IV. Course Materials
Has 3-5 core books
V. Course Schedule has three sections
1. Teaching
Does not have dates but class 1,2,3, etc
Each class has its assignments/readings. If not highlight
Has 30 hours of material
Format is not table like Viv, but like Riches
2. Practicum
3. Integration Day
VI. Learning and Assessment Activities
In a table with headings Number, Assessment Task, Maximum Mark Weighting
Numbers add up to 100 or 100%
VII. Expectations and Grading
has HBI, ATS, and APU set out separately
should be the same pretty much for all courses
VIII. Course Bibliography
All have same indent
In APA 5 format
All dates are in brackets after name of authors
Full stop (period) at end of each and after name, date, and title.
Single spaced
Hanging Indent
Sorted alphabetically or arranged in categroeis under bold subheading and sorted within each subheading
IX. Outcome Profile formatted from database