## Sheet1
STEP | PROCESS | TIME FRAME | KEY PLAYERS
PRE-CONSULTATION
Write Proposal | Collect all notes, data, and relevant research then format
Write Funder Letters | Write 5 letters of intent/request to send proposal
Request Papers/Case Studies | From the 5 locations including their philosophy, content, delivery mechanisms, and ideas of how to multiply the work
Define Content | For the materials, manual, and consultation
Revise Website | Update material and content
Plan Consultation | Develop and gather all materials, content, and presentations | Now - Nov. 19
Hold Consultation | Meet with pastors, present, listen to presentations, etc. | Nov. 20-24
Form Committee | Select/invite pastors and other leaders from consultation | Nov. 20-24
Meet with Committee | In person? Over Skype? How frequently? Discussing the Grassroots Learning Network
POST-CONSULTATION
Develop Manual | Determine topics, collect research and case studies |  | Committee
Format Manual | Develop attractive and easy-to-use manual formatting |  | Committee, (one specific person?)
Develop Dissemination Method | Use of mobile phone and tablet technology; run tests |  | Tech. savy committee member
Define personnel | What are the levels of personnel and what are their roles? |  | Committee
Select Starting Sites | Discuss which sites are best to start in |  | Committee
Select City Coordinators | Discuss and select/invite leaders to become City Coordinators |  | Committee
Select/Enlist Facilitators | Potentially enlist MATUL graduates, schools, faculty, etc. |  | Committee, City Coordinators
Select Trainers | From amongst the locals at each site |  | Facilitators
Train trainers | Use manual to train trainers of trainers |  | Facilitators, Trainers
Trainers form Groups | Starting with 15, decreasing to 10, training from manual |  | Facilitators, Trainers, Trainees
Record Data/Evaluate | How are the groups functioning? Is there multiplication? Any issues? |  | Facilitators, City Coordinators, Committee